## Sheet1
Working name |  | Member | Time(hour) | Status
Document | Setup environment |  | 8 | Done
| object table |  | 4 | Done
| ER diagram |  | 8 | Done
| Activity diagram |  | 36 | 15%
| Class diagram |  | 15 | Done
Coding | Helper |  | 30 | 20%
| Login |  | 4
| Logout |  | 1
| Account management |  | 6
| Category management |  | 4
| Product management |  | 4
| Print product info(pdf) |  | 4
| Log management |  | 2 |  | 25 | 6.25
Sum | 126 |  | 31.5